Q 1. Why is software development life cycle important?

ANSWER

The system development life cycle (SDLC), also know as application development life cycle or software development life cycle. It is a term used to describe a process for planning, desinging, executing, testing and deploying an information system in software engineeering.

- SDLC is a process followed for a software project, within a software organization.
- It consists of a detailed plan describing how to develop, maintain, replace and alter or enhance specific software.
- The life cycle defines a methodology for improving the quality of software and the overall development process.
- SDLC is a well-defined, structured sequence of stages in software engineering to develop the intended software product.

Q 2. Come up with Entry and Exit criteria for each phases ofproject management life cycle

ANSWER

Project management is the application of processes, methods, knowledge, skills and experience to achieve the project objectives. A project is a unique, transient endeavour, undertaken to achieve planned objectives, which could be defined in terms of outputs, outcomes or benefits.
The entry criteria deals with different materials which is used as the starting element in each phase.
The exit criteria deals with outcome of each phase..

Phase 1:Project Initiation

Entry criteria - business case it is define the project at a broad level.
Exit criteria - project initiation document (PID) that outlines the purpose and requirements	of the project.

Phase 2: Project Planning

Entry criteria - Setting goals are S.M.A.R.T. and CLEAR
Specific – To set specific goals, answer the following questions: who,	what, where, when, which, and why.
Measurable – Create criteria that you can use to measure the success	of a goal.
Attainable – Identify the most important goals and what it will take to	achieve them.
Realistic – You should be willing and able to work toward a particular	goal.
Timely – Create a timeframe to achieve the goal.
Exit criteria - project manager create different document such as

Scope Statement – A document that clearly defines the business need, benefits of the project, objectives, deliverables, and key milestones. A scope statement may change during the project, but it shouldn’t be done without the approval of the project manager and the sponsor.
- Work Breakdown Schedule (WBS) –This is a visual representation that breaks down the scope of the project into manageable sections for the team.
- Milestones – Identify high-level goals that need to be met throughout the project and include them in the Gantt chart.
- Gantt Chart – A visual timeline that you can use to plan out tasks and visualize your project timeline.
- Communication Plan – This is of particular importance if your project involves outside stakeholders. Develop the proper messaging around the project and create a schedule of when to communicate with team members based on deliverables and milestones.
- Risk Management Plan – Identify all foreseeable risks. Common risks include unrealistic time and cost estimates, customer review cycle, budget cuts, changing requirements, and lack of committed resources.
### Phase 3: Project Execution

Entry criteria – different kind of document which inclluding the meeting, status report, development update etc.
Exit criteria – detailed document which contain the total execution strategies.
### Phase 4: Project Performance/Monitoring

Entry criteria –key performance indicators (KPIs) to determine if the project is on track.
Exit criteria – performance measure document contain
Project Objectives: Measuring if a project is on schedule and budget is an indication if the project will meet stakeholder objectives.
- Quality Deliverables: This determines if specific task deliverables are being met.
- Effort and Cost Tracking: PMs will account for the effort and cost of resources to see if the budget is on track. This type of tracking informs if a project will meet its completion date based on current performance.
- Project Performance: This monitors changes in the project. It takes into consideration the amount and types of issues that arise and how quickly they are addressed. These can occur from unforeseen hurdles and scope changes.
### Phase 5: Project Closure

Entry criteria – contain total project information.
Exit criteria – documents contain lesions learned for this project.

Q 3. What are the roles of a Business Analyst? Why is Business Analysis crucial for a project success?

ANSWER

A business analyst works as a liaison among stakeholders in order to elicit, analyze, communicate, and validate requirements for change to business processes, policies, and information systems.
- Business Analysis Planning and Monitoring
- Elicitation
- Requirements Management and Communication
- Enterprise Analysis
- Requirement Analysis
- Solution Assessment
Business analyst define and discribe the project in initial stage.

Q 4. Define the roles and responsibilities of a Project Manager

ANSWER

- Takes ownership of the whole project
- Is proactive not reactive
- Adequately plans the project
- Is Authoritative (NOT Authoritarian)
- Is Decisive
- Is a Good Communicator
- Manages by data and facts not uniformed optimism
- Leads by example
- Has sound JudgementIs a Motivator
- Is Diplomatic
- Can Delegate